## Sheet1
Sl. No. | Topics | Estimate (hr) | Planned |  | Status | Completed Date |  | Remarks
|  |  | Start Date | End Date |  |  | Associates
1 | Edge.AI
| Overview | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Data pre-processing | 0.5 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Model training and inference walkthrough | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Code walkthrough | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Setup and execution | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Jetson Deployment | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
| Reverse KT | 1 | 2023-09-08 | 2023-09-08 | Done | 2023-09-08 | Nikila, Varshini, Prateek
2 | RideBuddy
| Overview | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
| Data pre-processing | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
| Model training and inference walkthrough | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
| Code walkthrough | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
| Setup and execution | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
| Reverse KT | 1 | 2023-09-07 | 2023-09-07 | Done | 2023-09-07 | Vaishnavi, Prateek
3 | GROW
| Overview | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
| Data pre-processing | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
| Model training and inference walkthrough | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
| Code walkthrough | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
| Setup and execution | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
| Reverse KT | 1 | Feb | Feb | Done | Feb | Shantanu, Harshavardhan | No Formal KT but files and codebase was pushed to GIT and necessary information passed
4 | VQI
| Overview | 1 | 2023-07-19 | 2023-07-19 | Done | 2023-07-19 | Shashank, Varshini | No Formal KT but files were shared and necessary information passed
| Setup and execution | 1 | 2023-07-19 | 2023-07-19 | Done | 2023-07-19 | Shashank, Varshini | No Formal KT but files were shared and necessary information passed
| Reverse KT | 1 | 2023-07-20 | 2023-07-20 | Done | 2023-07-19 | Shashank, Varshini | No Formal KT but files were shared and necessary information passed
5 | AutoQC
| Overview | 1 | 2023-06-02 | 2023-06-02 | Done | 2023-06-02 | Nikila | No Formal KT but files were shared and necessary information passed
| Setup and execution | 1 | 2023-06-02 | 2023-06-02 | Done | 2023-06-02 | Nikila | No Formal KT but files were shared and necessary information passed
| Reverse KT | 1 | 2023-06-02 | 2023-06-02 | Done | 2023-06-02 | Nikila | No Formal KT but files were shared and necessary information passed