## Sprint4-Summary
ID | Work Item Type | Title | Responsible | Reason for Spill-over | Spill-Over
66 | Epic | Digital Twin Foundation Implementation | Ashok Mallya
17 | User Story | Deployment of Code into Specific Azure Services | Akshit Gupta | NA | No
37 | User Story | Data archival services | Krishnendu Kar | NA | No
84 | User Story | Logging in Microsoft Defender | Krishnendu Kar | NA | No
65 | Epic | MVP for Gas Turbine and Cooling Tower Fan | Ashok Mallya
1141 | User Story | Low-Frequency pipeline deployment | Kaushik Vishwas | Scope-change to focus only on low-frequency data here, #1145 - Change in the Pump model, hence moving to Sprint5, #1207 - Development of Function-App for Low-Frequency: Facing proxy issue, which needs to be resolved (work-in-progress) | Yes
1225 | User Story | Data Archival - implementation | Krishnendu Kar | Separation of user-story for strategy/decision and implementation, so sort of re-planned | Yes
63 | User Story | Fault insights for gas turbine bearing (Operational Insights) | Saurabh Sharma | Fault Model Deployment is still in progress, Data flow to dashboard via API will only be available post that, hence moving the user story to sprint 5 | Yes
47 | User Story | MVP for Thrust Bearing Gas Turbine |  | NA | No
55 | User Story | Fault detection model development for cooling tower |  | NA | No
59 | User Story | Model Development for Induction Motor based on Synthetic Data |  | NA | No
971 | User Story | MVP for Journal Bearing Gas Turbine | Harshavardhan Amirthalingam | API related changes and testing and validation is pending to be implemented | Yes
127 | Epic | MVP for pump | Ashok Mallya
977 | User Story | Simulation Model deployment and validation | Derisala Ramakrishna | Duplicate and NA
61 | User Story | Simulation Model Generation and Validation - Pump | Derisala Ramakrishna | CR - is work-in-progress, to be shared from DT-Bosch team and related approvals to be in-place. | Yes
979 | User Story | Motor health indexing(Pump) and fault monitoring using MCSA approach | Harshavardhan Amirthalingam | NA
1224 | User Story | Simulation data generation for pump water-hammer effect | Derisala Ramakrishna | Input data not received | Yes
987 | User Story | Fault modeling for pumps | Harshavardhan Amirthalingam | Planned for Sprint6, as Pump related topic needs CR approval and then can get implemented(Needed re-planning) | Yes
978 | User Story | Simulation data generation for pump cavitation | Derisala Ramakrishna | Planned for Sprint6, as Pump related topic needs CR approval and then can get implemented(Needed re-planning) | Yes
Not tagged to deliverable/Milestone
31 | User Story | Data governance | Ashok Mallya | On-going continous topic | Yes
963 | User Story | ADO - Migration | Krishnendu Kar | As it was an open issue, needs close tracking | Yes
24 | User Story | Security Engineering Process - Step2 | Bhatt Satish Chandra | NA | No
1070 |  | Fluid domain extraction |  | Removed, as it was re-planned

## Sprint5-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over | Comments
65 | Epic | MVP for Gas Turbine and Cooling Tower Fan | Ashok Mallya
1141 | User-story | Low-Frequency pipeline deployment | Vishwas Kaushik | Closed | NA
63 | User-story | Fault insights for gas turbine bearing (Operational Insights) | Saurabh Sharma | Closed | NA
971 | User-story | MVP for Journal Bearing Gas Turbine | Vishwas Kaushik | Closed | NA
1212 | User-story | Baseline fault model for the assets - Gas Turbine, Cooling Fan | Harshavardhan Amirthalingam | Closed | NA
1225 | User-story | Data Archival - implementation | Krishnendu Kar | Closed | NA
1268 | User-story | High-Frequency pipeline deployment - Cooling Fan | Vishwas Kaushik | Spill-over |  | 1328 - Modify ADX to accommodate output response(Dependency on pipelines and models which are work in-progress)
127 | Epic | MVP for pump | Ashok Mallya
61 | User-story | Simulation Model Generation and Validation - Pump | Derisala Ramakrishna
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over |  | Re-planned to consider in Sprint 6, at the beginning of Sprint 5
1269 | User-story | High-Frequency pipeline deployment - Pump | Vishwas Kaushik | Spill-over |  | Re-planned to consider in Sprint 6, at the beginning of Sprint 5
1224 | User-story | Simulation data generation for pump water-hammer effect | Derisala Ramakrishna | Spill-over |  | Re-planned to consider in Sprint 6, at the beginning of Sprint 5
978 | User-story | Simulation data generation for pump cavitation | Derisala Ramakrishna | Spill-over |  | Re-planned to consider in Sprint 6, at the beginning of Sprint 5
|  | Non-Functional | Ashok Mallya
1367 | User-story | Cost optimization for PPGPL Dev subscription | Krishnendu Kar | Closed | NA
1362 | User-story | Change in data acquisition for PPGPL | Krishnendu Kar | Spill-over |  | Team is working on ODBC Driver installation on Azure VM. This will be a parallel activity (without hampering any milestones). As this will change data acquisition for DT as well as non-DT tracks together(Email from Raj attached here)
963 | User-story | ADO - Migration - Step1 | Krishnendu Kar | Closed | NA | Changed the scope but concluded
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Spill-over |  | As there is no specific DSO for the region of T&T, team is exploring on options to contact external counsel( PS: This is for all tracks, not DT alone) - Ashok has aligned with Gulshan here
1370 | User-story | Security Engineering Process - Step3 | Bhatt Satish Chandra | Spill-over |  | Security testing - is work in-progress

## Sprint6-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over
65 | Epic | MVP for Gas Turbine and Cooling Tower Fan | Ashok Mallya
1268 | User-story | High-Frequency pipeline deployment - Cooling Fan | Vishwas Kaushik | Closed | NA
127 | Epic | MVP for pump | Ashok Mallya
978 | User-story | Simulation data generation for pump cavitation | Derisala Ramakrishna | Closed | NA
987 | User-story | Fault modeling for pumps | Harshavardhan Amirthalingam | Closed | NA
1224 | User-story | Simulation data generation for pump water-hammer effect | Derisala Ramakrishna | Closed | NA
1269 | User-story | High-Frequency pipeline deployment - Pump | Vishwas Kaushik | Closed | NA
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over | As #1659 is pending to be executed, moved to Sprint 7. For details please check the comments of #1659
126 | Epic | Digital Twin IAPM Dashboard (Visualization & Finalization) | Ashok Mallya
1467 | User-story | Live and Historic Sensor data | Sharma Saurabh | Closed | NA
1660 | User-story | Event-History implementation | Akshit Gupta | Closed | NA
1466 | User-story | Alerts and notification | Akshit Gupta | Spill-over | Except "Template Finalization for notification for email", rest all tasks are yet to be actioned
1468 | User-story | Integration of the Digital Twin-IAPM dashboards to the Intelligent Enterprise Business Dashboard | Sharma Saurabh | Spill-over | As it is part of Milestone 5, re-planned to execute in Sprint 7
1654 | User-story | Common-causes of failure | Sharma Saurabh | Spill-over | #1657 - Technical issues faced - team is working on the same, should be resolved at the earliest
|  | Non-Functional | Ashok Mallya
1370 | User-story | Security Engineering Process - Step3 | Bhatt Satish Chandra | Closed | NA
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Spill-over | Aligning wrt Data Governance topic internally at Bosch for T&T Region
1506 | User-story | ADO Migration - Step2 | Krishnendu Kar | Spill-over | Details in the comments section in ADO
1362 | User-story | Change in data acquisition for PPGPL | Krishnendu Kar | Spill-over | Details in the comments section in ADO

## Sprint7-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over
127 | Epic | MVP for pump | Ashok Mallya
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over | Identification of probable Water-hammer effect - pending to be executed. Details in the ADO.
126 | Epic | Digital Twin IAPM Dashboard (Visualization & Finalization) | Ashok Mallya
1654 | User-story | Common-causes of failure | Sharma Saurabh | Closed
1466 | User-story | Alerts and notification - email | Akshit Gupta | Closed
1468 | User-story | C-Suite related changes | Sharma Saurabh | Closed
|  | Non-Functional | Ashok Mallya
2352 | User-story | Points from test version1 demo | Ashok Mallya
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Spill-over | As there is no specific DSO for the region of T&T, team is exploring on options on this. This is for all tracks, not DT alone.
1362 | User-story | Change in data acquisition for PPGPL | Krishnendu Kar | Spill-over | Discussions in-progress, Jason has proposed options and a concrete decision is yet to be taken(Please refer email from Jason - dated 04/01/2023 with subject - Draft: ODBC Connectivity to )
1506 | User-story | ADO Migration - Step2 | Krishnendu Kar | Spill-over | This is an on-going process where all the delta changes need to be pushed to PPGPL as well as PPGPL-Bosch organization
2158 | User-story | Security Engineering Process - Step 4 | Bhatt Satish Chandra | Spill-over | OSS Scan is in-progress, should conclude in Sprint 8

## Sprint8-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over
127 | Epic | MVP for pump | Ashok Mallya
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over | Identification of probable Water-hammer effect - pending to be executed. Details in the ADO.
126 | Epic | Digital Twin IAPM Dashboard (Visualization & Finalization) | Ashok Mallya
2630 | User-story | Integration of the Digital Twin-IAPM dashboards to the Intelligent Enterprise Business Dashboard | Ashok Mallya | Closed | API will be shared with UI/UX team for integration into IEBD
|  | Non-Functional | Ashok Mallya
2352 | User-story | Points from test version1 demo | Ashok Mallya | Spill-over | OSS Scan is in-progress, should conclude in Sprint 8
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Spill-over | Discussions with Data Governance team in-progress, DPN has been shared with customer for review and update wrt PPGPL guidelines. Once this is available the same would be loaded onto the home page.
1362 | User-story | Change in data acquisition for PPGPL | Krishnendu Kar | Closed
1506 | User-story | ADO Migration - Step2 | Krishnendu Kar | Closed
2158 | User-story | Security Engineering Process - Step 4 | Bhatt Satish Chandra | Closed

## Sprint9-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over
127 | Epic | MVP for pump | Ashok Mallya
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over | Simulation: Impeller creation , cavitation and Vibration is work in-progress and Identification of probable Water-hammer effect - pending to be executed(this is dependent on Simulation)
|  | Non-Functional | Ashok Mallya
2352 | User-story | Points from test version1 demo | Ashok Mallya | Spill-over | OSS Scan is in-progress, report is expected by 05-Feb-2024. Hence moving to Sprint 10
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Spill-over | As this topic is common to all tracks, TPO sales team to kindly take care. Discussions with Rajesh Rajput done in this regard. Action from TPO awaited.
3165 | User-story | Change in data acquisition for PPGPL - open point | Krishnendu Kar | Closed | Editing the source code in the ADF pipeline task is on-hold, so closing this user-story temporarily.
2158 | User-story | Security Engineering Process - Step 5 | Bhatt Satish Chandra | Closed

## Sprin10-Summary
ID | Work Item Type | Title | Responsible | Status | Reason for Spill-over
127 | Epic | MVP for pump | Ashok Mallya
1271 | User-story | Baseline fault model for the asset - Pump | Harshavardhan Amirthalingam | Spill-over | Simulation: Impeller creation , cavitation and Vibration is work in-progress and Identification of Impeller Cavitation(Data-Science topic) - pending to be executed(this is dependent on Simulation)
|  | Non-Functional | Ashok Mallya
2352 | User-story | Points from test version1 demo | Ashok Mallya | Closed
31 | User-story | Data governance | Arvind Kumar Chandrashekaran | Closed
3722 | User-story | Training Sessions | Ashok Mallya | Closed
3660 | User-story | Security Engineering Process - step6 | Bhatt Satish Chandra | Spill-over | Pen-test is pending