## Sheet1
Tasks | Responsible | Due Date
Cloud infrastructure costs to be considered for Year-3, 4 ( depending on development requirements) | Arjun | 2024-11-09
Additional development efforts are required for stabilization. Development efforts needs to be revisited for year-2,3 | Arjun | 2024-11-09
3-tier based pricing model was agreed upon. However, $15,000 per year seems low—further evaluation is necessary | Subham | 2024-11-09
Pricing model should clearly demonstrate the value and benefits gained from the investment | Subham | 2024-11-09
Further to work on market research to understand competitor pricing, also explore on the support model provided by competitors | Subham | 2024-11-07
Market based Pricing | Subham | 2024-11-07
Explore PTC Thingworx IoT solution & check for relevancy with our IndAiGenious product | Subham | 2024-11-07
To have 1-2 Anchor Customers, to further explore with Syntegon on opportunities for MVP/PoC | Subham/Arjun | 2024-11-09
Engage with the Building Tech team for further discussions. | Harsha | 2024-11-07
Contents on what will customers be receiving in each Support Plan | Arjun | 2024-11-09

## Sheet2
Work Item | Deliverables
Epic | Milestone 1 : Completion of Digital Twin Foundation Design
UserStory | Detail technical discussion on the Pump & Engineering requirement freeze
UserStory | Detail technical discussion on the Gas turbine & Engineering requirement freeze
UserStory | Detail technical discussion on the cooling tower Areas & Engineering requirement freeze
UserStory | Setup of Edge server, configuring gateway software, establishing data extraction system from PHD
UserStory | Data transformation
UserStory | Data contextualization
Epic | Milestone 2 : Completion of Digital Twin Foundation Implementation
UserStory | Device management (Azure Infra setup)
UserStory | System monitoring and alerting
UserStory | Collaboration with UX team for Intelligent Enterprise Dashboard Integration
UserStory | Logging
UserStory | Data governance (Initiated the process with Data Security Officer for Data Governance)
UserStory | Data encryption
UserStory | Device and data security
Epic | Milestone 3 : Implementation of WP 14 (MVP for Gas Turbine) & WP 15 (MVP for Cooling Tower Fan)
UserStory | Sensorization of Gas Turbines (PPGPL) Available on GT
UserStory | Fault modeling/ prediction for Gas turbine bearings
UserStory | Simulation Model Generation
UserStory | Model Validation
UserStory | Sensorization of Heater Fan (PPGPL)
UserStory | Data twin development for cooling tower (Data and feature visualization)
UserStory | Fault detection model development for cooling tower : Synthetic Data will be used as per SOW2
UserStory | Model deployment and validation
Epic | Milestone 4 : Implementation of WP 13 ( MVP Pump )
UserStory | Sensorization of Pump & Motor: MCSA (PPGPL)
UserStory | Simulation data generation for pump cavitation & water hammer effect#
UserStory | Motor Health Indication of Motor using MCSA Approach (Synthetic Data)
UserStory | Fault modeling for pumps (Synthetic Data)
UserStory | Model Validation
Epic | Milestone 5 : Digital Twin IAPM Dashboard (Visualization & Finalization) Partially
UserStory | Alerts and notification
UserStory | Fault insights of pump cavitation & water hammer effects
UserStory | Fault insights for gas turbine bearing
UserStory | Faults insights for cooling tower fan
UserStory | Integration of the Digital Twin-IAPM dashboards to the Intelligent Enterprise Business Dashboard In Progress
UserStory | System Integration & Testing
UserStory | IAPM dash-board configuration & Delivery of Test Version -1 Demo MVP (Live Demo of Dashboard )